## Head office Report
Sedra Phase 1 B -Roshn Project
14/6/2026
Saudi-Icon
Foreman /Supervisor /Leadman -11 | 11
Scaffolders Inspector- 2 | 2
Rigger- 0
Helper- 8 | 8
Tile Mason- 10 | 10
Electrician- 14 | 14
Plumber- 7 | 7
Scaffolder - 0
Duct - 0
Gypsum installer- 5 | 5
Painter- 13 | 13
Surveyor- 02 | 2
Store Keeper- 02 | 2
Hse Officer -05 | 5
Wood Factory Carpenter -0
Rentals
Helper (Azam)- 40 | 40
Delowar
Shuttering Carpenter -5 | 0
Steel Fixer -4
Mithal Al Shamal
Mason- 8
Labor- 6 | 22
scaffolder- 8
Sub-contractor details
Alfa -
Mason -8 | 8
Labor -12 | 12
Osoul For Advance Project
Mason -13 | 13
Labor -17 | 17
Qasrcom General Contracting EST
Mason -31 | 31
Labor -27 | 27
Integrated Sub contractor
Mason -0 | 0
Labor -0
PAC
Mason -17 | 17
Labor -16 | 16
NOF
Mason -3
Labor -3 | 6
ALI
Mason -8
Labor -14 | 22
Ehcons Elegant Home Construction
Mason -3 | 5
Labor -2
MEP Contractors -21 | 22
196
Saudi-Icon:- 74
Rentals:- 71
Sub-contractor:- 196
Total:- 341

## Site Report
Sedra Phase 1 B -Roshn Project
14/6/2026
Saudi-Icon
Office Staff
Project Director -1 | 1
Project Manager -02 | 2
Safety Manger - 01 | 1
Mep Manager -1 | 1
QA/QC Manager -1 | 1
Planning Engineer -01 | 1
Document Controller -02 | 2
Draftsman -1 | 1
Quantity surveyor -01 | 1
Technical Architecture Engineer -01 | 1
Office Boy -01 | 1
Office Cleaner -01 | 1
Site Staff
Construction Manager -02 | 2
Site Engineer -06 | 6
Electrical Site Engineer -1 | 1
Mechanical Engineer -01 | 1
Chief Surveyor -0
Site Supervisor -01 | 1
Electrical Supervisor -01 | 1
Electrical Foreman -01 | 1
Mechanical Supervisor -03 | 3
General Foreman -05 | 5
Land Surveyor -02 | 2
QA/QC -03 | 3
Mep QA/QC Engineer -01 | 1
QA/QC Electrical -01 | 1
Safety Officer -04 | 4
Driver -04 | 4
Envirementol Co -Ordinator -01 | 1
Mechanical Inspector -0
HSE Admin -1 | 1
Logistic Officer -01 | 1
Team Leader -01 | 1
Scaffolders Inspector- 2 | 2
Rigger- 0
A/C Technician- 0
Helper- 07 | 7
Block Mason- 0
Mason-Tiler- 9 | 9
Electrician- 14 | 14
Plumber- 7 | 7
Scaffolder - 0
Duct - 0
Gypsum installer- 5 | 5
Painter- 13 | 13
Surveyor Labor- 02 | 2
Store Keeper- 02 | 2
Ass Store Keeper- 01 | 1
116
Rentals
Helper (Azam)- 38 | 38
Delowar
Shuttering Carpenter -09 | 9
Steel Fixer -04 | 4
Mithal Al shamal
Mason -8 | 8
Labor - 8 | 8
scaffolder-11 | 11
78
Sub-contractor details
Alfa
Mason -18 | 18
Labor -17 | 17
Osoul For Advance Project
Mason -3 | 6
Labor -3
PAC
Mason -7 | 14
Labor -7
Qasrcom General Contracting EST
Mason -7 | 7
Labor -6 | 6
ALI
Mason -6 | 6
helper- 8 | 8
Architechtural plan co
Mason -5 | 5
helper- 5 | 5
NOF
Mason -3 | 3
helper- 3 | 3
Integrated Construction Solution
Mason -3 | 3
Labor -5 | 5
Arkan
Mason -7 | 15
Labor - 8
Energy exit Trading
Mason- 2 | 4
Labor- 2
Arvio
Mason- 6 | 10
Labor- 4
Construction Plans co | 3
Mason- 1
Labor- 2
Noujoum Al Tasmeem | 4
Mason- 2
Labor- 2
MEP Subcontractor
Inarco, Kiara, Abu basher, Mgcc
Electrician- 24 | 30
Forman/Staff- 6 | 13
Plumber- 13
Saudi-Icon:- 116 | 185
Rentals:- 78
Sub-contractor:- 185
Total:- 379

## Update list
S # | Name # | Designation # | EMP ID #
1 | Mohammad El Barakeh | Project Director | 2478
2 | Mohannad Halaweh | Project Manager | 1927
3 | Mohannad Hanash | Project Manager | 1272
4 | Karim Mostafa | Construction Manager | 1835
5 | Mohammed Al Obwayni | Construction Manager | 3397
6 | Muhammad Ashfaq | Mep QA/QC Engineer | 4950
7 | Ahmad Hasni | Quantity Surveyor | 4968
8 | Abdul Qader Julayyil | Site Mep Manager | 4945
9 | Mujeeb ullah | QA/QC Engineer | 3783
10 | Jan Dastagir | QA/QC Engineer | 3801
11 | Sardar Nayab | QA/QC Engineer | 4585
12 | Ahmed Azzam | Document Controller | 3810
13 | Jaheer | Document Controller | 4937
14 | Mahmoud Awad | Senior Planning Engineer | 4939
15 | Ali Hassan Anwar | Site Engineer | 4575
16 | Mohammad Gunaimat | Site Engineer | 4956
17 | Abdellah al hasan | Site Engineer | 4959
18 | Abdallah Al Baz | Site Engineer | 4948
19 | Riyad al zahirini | Site Engineer | 4972
20 | Rizwan Aamir | Site Engineer
21 | Mohammad Shaheer | Hse Manager | 1266
22 | Layan Qahtani | Hse Officer | 4938
23 | Raja Muhammad Osama | Hse officer | 4584
24 | Adeel Asghar | Hse Officer | 4581
25 | Abdul Fawad Kasma | Hse Officer | 4949
26 | Mohd Faiq Ali | Hse Officer | 4952
27 | Samiullah Ehsan | Environmental Engineer | 2743
28 | Thaslim Hassan | Logistic -Co ordinator | 2751
29 | Salem Badr | Logistic -Co ordinator | 2694
30 | Obada Al Doum | Mechanical Engineer | 4953
31 | Syed Fahad Shah | Mechanical Engineer | 4958
32 | Raafat Nady | Mechanical Supervisor | 4944
33 | Muddaser Shaukat | Mechanical Supervisor | 4954
34 | Mohammad Tulimat | Mechanical Foreman | 1908
35 | Yahdia Raghoua | Site Supervisor | 1435
36 | Ayman Raafat | Site Supervisor | 3753
37 | AbdelKarim Khairi | General Foreman | 4077
38 | Khalid Halim | General Foreman | 4064
39 | Mahib Al Wadi | General Foreman | 3336
40 | Waseem Aftab | General Foreman | 4816
41 | Abdulla Al Ahdal | General Foreman | 1906
42 | Adnan Shakeel | General Foreman | 4744
43 | Ridha Ibrahim | Electrical Supervisor | 4947
44 | Ibrahim Salah | Electrical Foreman | 2452
45 | Adil | Timekeeper | 4444
46 | Al Amin Miah | Scaffolding Inspector | 4540
47 | Mamun Abul Hasem | Scaffolding Inspector | 4568
48 | Obaid Raza | Surveyor | 3329
49 | Abdelrahman Al Madani | Surveyor | 3235
50 | Muhammad Akhlaq | Surveyor | 3792
51 | Jakir Mohammad | Storekeeper | 4403
52 | Durgesh Kumar | Storekeeper | 4376
53 | Mohammad Akram | Procurment | 4961
54 | Basheer Al Waeli | Runner | 2051
55 | Nadeem Haider | Driver | 3049
56 | Muhammad Tanweer | Driver | 4897
57 | Jumir Khan | Driver | 3850
58 | MD Salman | Helper | 2419
59 | Yahya Al Khali | Helper | 2300
60 | Mansoor Al Qadi | Helper | 2462
61 | Ruhul Amin | Helper | 4087
62 | Ariful Islam | Helper | 2157
63 | Ashraf khan | Helper | 3129
64 | MD Kauchar Mia | Helper / Team Leader | 2336
65 | MD Rakib | Helper -Surveyor | 4095
66 | MD Minto Hosen | Helper -Surveyor | 4086
67 | Ram Sebak thakur | Gypsum Installer | 2168
68 | Ajab Kumar | Gypsum Installer | 2542
69 | Pran Chandra | Gypsum Installer | 2592
70 | Yousuf Ait Hasnain | Gypsum Installer | 4075
71 | Abdel kareem ait ba | Gypsum Installer | 4496
72 | Rehan Khan | Electrician | 2908
73 | Shofiqul Islam | Electrician | 1857
74 | Keyamudden Ansari | Electrician | 1950
75 | Mohammad Kalamuddin | Electrician | 2968
76 | Mohammad Ajaj | Electrician | 2969
77 | Mohammad Nasim | Electrician | 2975
78 | Jawed Alam | Electrician | 2833
79 | Naushad Ali | Electrician | 4038
80 | Abdulmuez Al Maswari | Electrician | 3579
81 | Hare Ram | Electrician | 1874
82 | Samsuddin Ansari | Electrician | 4395
83 | Haider Ali | Electrician | 3053
84 | Bikash Gurung | Electrician | 1893
85 | Aphatab Ansari | Electrician | 3054
86 | Poochi Padayachi | Plumber | 2498
87 | Nadeem Ashraf | Plumber | 4731
88 | Arif Ali | Plumber | 2199
89 | Mohammad Vasim | Plumber | 4373
90 | Hafiz Muhammad | Plumber | 4807
91 | Wakil Ahmad | Plumber | 4028
92 | Vijay Kumar | Plumber | 3267
93 | Ibrahim | Painter | 2898
94 | Nasir | Painter | 4725
95 | Rakib | Painter | 4345
96 | Alam Ansari | Painter | 3076
97 | Dev Narayan Mahto | Painter | 4203
98 | Jhajeb | Painter | 4864
99 | Foridul Islam | Painter | 4550
100 | Lalan | Painter | 2015
101 | Shabrul Islam | Painter | 4569
102 | Sohel Mia | Painter | 2723
103 | MOHAMMAD ALAUDDIN | Painter | 2807
104 | KRISHNA KUMAR | Painter | 2955
105 | LALIT KUMAR | Painter | 4159
106 | HARUN MUSLMAN | Painter | 4162
107 | SALUDDIN DEEWAN | Painter | 4299
108 | TAMIM MIA | Painter | 4339
109 | Abdel Rahman Khokar | Mason-Tiler | 4126
110 | Sabir Mohammad | Mason-Tiler/Store | 4129
111 | Ilphan Gauri | Mason-Tiler | 4125
112 | Serjul Islam | Mason-Tiler | 2800
113 | Masum Rana | Mason-Tiler | 2801
114 | Irshad | Mason-Tiler | 4657

## Floor & Building wise
Sedra Phase 1B -Roshn |  |  | 08.06.2026
Alfa
|  | Mason | Labor
Building -64 | Ground Floor | 0 | 0
| Level -01 | 4 | 6
| Level -02 | 3 | 4
| Level -03 | 0 | 0
Building -67 | Ground Floor | 0 | 0
| Level -01 | 4 | 4
| Level -02 | 2 | 3
| Level -03 | 0 | 0
Total |  | 13 | 17
Osul For Advance Project and Pac
|  | Mason | Labor
Building -68 | Ground Floor | 1 | 1
| Level -01 | 5 | 5
| Level -02 | 0 | 0
| Level -03 | 2 | 2
Building -69 | Ground Floor | 0 | 0
| Level -01 | 5 | 5
| Level -02 | 0 | 0
Total |  | 13 | 13
PAC
|  | Mason | Labor
Building -74 | Ground Floor | 0 | 0
| Level -01 | 2 | 2
| Level-02 | 1 | 1
Building -71 | Ground Floor | 2 | 2
| Level -01 | 0 | 0
| Level -02 | 0 | 0
| Level -03 | 0 | 0
Total |  | 5 | 5
QGC & Mithal (Rental)/PAC
|  | Mason | Labour
Buiilding 66 | Ground floor | 1 | 1
| Level -01 | 2 | 3
| Level -02 | 6 | 6
| Level -03 | 3 | 3
Total |  | 12 | 13
QGC & Mithal (Rental)
|  | Mason | Labor
Building -65 | Level -01 | 0 | 0
| Level -02 | 14 | 11
| Level -03 | 3 | 2
Total |  | 17 | 13
ALI/ QGC
|  | Mason | Labor
Building -72 | Ground Floor | 0 | 0
| Level -01 | 0 | 0
| Level -02 | 0 | 0
| Level -03 | 3 | 4
Building -73 | Ground Floor | 0 | 0
| Level -01 | 1 | 1
| Level -02 | 1 | 1
| Level -03 | 4 | 6
Total |  | 9 | 12
Integrated construction solutions &ARKAN AL MAKAN
|  | Mason | Labor
Building -80 | Ground Floor | 0 | 0
| Level -01 | 2 | 3
Building -81 | Level -01 | 5 | 5
| Total | 7 | 8
PAC/NOF/ALI
|  | Mason | Labor
Building -70 | Ground Floor | 1 | 1
| Level -01 | 3 | 3
| Level -02 | 3 | 4
Total |  | 7 | 8
Rental
Delowar | Shuttering Carpenter |  | 0
| Steel Fixer |  | 0
Azam | Helper |  | 34